## Database
Florida's Turnpike Enterprise Design Lessons Learned
Project
Entry |  |  | FTE |  | Design |  |  |  | Primary
Date | Contract | FPID | Construction PM | Design PM | Firm | Description | Source | Key Words | Discipline | Issue Summary | Lessons Learned
2014 | E8M52 | 429330-1 | Ken Hudson | James Kervin | Wantman Group | Indiantown Road Interchange Improvements | Construction - Extinguish the Torch Session III Report | Signing | Traffic Design | Existing median separator for Indiantown Rd. is 6’ wide with architectural pavers. The Contract Plans specified 36” wide sign panels which would breach the standard 2’ minimum clear space from the edge of sign panel to the face of curb. This standard requirement is important to maintenance as these signs are hit often. Also, the exit gore sign was indicated by pay item 700‐20‐15. The EOR chose this pay item due to the sign panel size of 6’‐6” x 5’‐0”, or 32.5 SF. However, the Design Standard 11860 “Single Column Ground Signs” does not accommodate a panel size greater than 30 SF or width exceeding 60". At 78” wide, the sign requires a special design. The solution at the time of discovery was to proceed with a multi‐column sign assembly per current Design Standards. | The EOR should ensure sign design standards are achievable when specifying sign panel sizes.
2014 | E8M79 | 431079-1, 431079-3 | Ken Hudson | Terry Miller | Moffatt & Nichol | Resurface Mainline from Glades Rd. (MP 76.2) to S. of Atlantic Ave. (MP 81.1) | Construction - Extinguish the Torch Session III Report | Pavement Markings | Traffic Design | The shoulder width throughout the project varied from 10’ standard (+/‐) 0”‐8”, which made it difficult to maintain the standard detail. This was even more of a challenge at bridge approaches as well as at the beginning and ending of the project limits. | For bridge approaches the EOR should prepare a typical detail that tapers the FC to meet the existing bridge edge line configuration in order to keep the edge line completely on the FC and maintain compliance with the index requirements.
2015 | E8L90 | 423199-1, 423199-3 | Joseph Chinelly | Craig Bostic | Kimley-Horn | Resurface Polk Pkwy. from MP 8.1 to MP 21.7 | Construction - Extinguish the Torch Session III Report | Pavement Markings | Traffic Design | The contractor re-striped the final lift of structural course according to the Contract Plans. A Plan revision was then issued, calling for the friction course to be striped with a new configuration. Since the contractor placed frication course one lane at a time it would result in one lane being striped according to the revision and the other lane(s) striped according to the old configuration, creating conflicting striping in several areas. The contractor was required to hydro-blast striping from final lift of structural course and have it re-striped according to the new configuration. | EOR should specify in the Contract Plans that any reconfiguration of existing striping should be implemented immediately following the initial milling and resurfacing.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Noise Impacts | Tolls Design | The original Contract Plans did not require the generator enclosures to be noise attenuating. For most locations along the corridor this was not an issue; however, at one exit ramp, there is a residential home within 40 feet of the new equipment building site. Decibel readings at the property line were significantly above an acceptable threshold. | The EOR should review the locations of the equipment buildings and associated appurtances. In urban areas, with residential properties in close proximity, noise abatement measures for equipment should be considered. Consider potential update to the GTR.
2015 | E8M77 | 406151-4 | Ernest Garcia | Tom Neyer | AECOM | All Electronic Toll (AET) Phase 6B | Construction - Extinguish the Torch Session III Report | Power Service | Tolls Design | The Contract Plans for the electrical service show one electrical transformer at each toll equipment building site. At 2 sites the contract plans identified two separate electrical service meters, one installed at the equipment building and one installed for the ITS system but the 2 equipment building sites were constructed as designed with a single transformer at each building. The FTE General Tolling Requirements (GTR) requires that the toll equipment building and the ITS systems must be fed from separate electrical transformers. | The EOR should ensure that the Contract Plans incorporate all current GTR requirements in the original Design Plans. Specifically, the Contract Plans need to indicate separate electrical transformers for the Tolling Systems and for ITS components.
2016 | E8N37 | 431123-1 | Todd Kelly | Pamela Nagot | WBQ | Polk Parkway Painting of Bridges 160257, 160258 and 164507 | Construction - Extinguish the Torch Session III Report | Concrete Surface Finishes | Structures Maintenance | The scope of work called for the concrete surfaces to be cleaned in accordance with FDOT Standard Specification Section 400-19, which includes removal of loose coatings. The existing concrete coating was damaged by pressure washing, with the resulting cleaned surface having a very inconsistent or aged appearance. New Class 5 concrete coating was excluded from the original contract. | The EOR should evaluate the need for new Class 5 coating when adhesion of the existing coating is identified to be inconsistent during the existing conditions assessment. The new Class 5 work can be deleted if the cleaning does not damage the existing concrete surface coating.
2017 | E8Q16 | 435406-1 | Roxanne Riggs | Marco Barbarossa | Protean | Mainline Spur Painting of Bridges 870701, 870702 | Turnpike Structures | Project Team Staffing | Structures | Project team did not include structures staff. | Although there was no structural design tasks associated with the bridge painting, there was several structural POST-design tasks for which the EOR needed a structural engineer. These included review of containment shop drawings and submittals for construction loads on the bridge. EOR should have structures staff on the team for bridge painting projects.
2017 | E8N67 | 415051-4 | Ken Hudson | Paul Naranjo | Wantman Group | Widen HEFT Bird Rd. to SR 836 (Design-Build) | Turnpike Structures | Mass Concrete | Structures | Mass concrete was not identified in the plans. | For design-bid-build projects, the EOR designates elements that are mass concrete (as defined by the SDG) by use of the proper pay item numbers. This then triggers the required Specifications sections in construction for mass concrete. For design-build projects, the EOR is to identify mass concrete (as defined by the SDG) with plan notes that require use of the proper Specifications sections. Identification in either case requires calculations of volume to surface ratios. Mass concrete should be identified and should conform to all appropriate requirements of the Specifications regardless of project type. The only difference is how it is designated in the plans.
2017 | E8M60, E8M62, E8M63 | 431275-1, 406152-1, 406151-1 | Tracie Rose, Fernando Gomez | Tom Neyer | AECOM | Widen Veterans Expy. Sections 1-3 | Construction - Extinguish the Torch Session II Report | Open Flume | Drainage | An open flume was constructed on a 1:2 slope and did not have curb details which resulted in water flowing over the ditch pavement which eroded the 1:2 slope. | The EOR should consider a shoulder inlet system rather than an open flume. If an open flume is determined to be the best option, it should be very carefully considered on slopes steeper then 1:6 and should be sized to contain the 10-year storm.
2019 | E8Q41 | 435165-1, 435165-3, 435167-1, 435167-3 | Christopher NeSmith | Steve Soldati | CES | Resurface Mainline in Okeechobee & Indian River Counties from MP 178.2 to MP 185.0 | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | Base failures occurred in deep mill asphalt sections. A contributing factor was determined to be insufficient cooling time for the thick asphalt mat. After evaluating a test section, it was determined that 6 hours was the max cooling time. | For projects where there is a potential for base failures, the EOR should account a 6-hour cooling in the design of the traffic control plans.
2019 | E8Q41 | 435165-1, 435165-3, 435167-1, 435167-3 | Christopher NeSmith | Steve Soldati | CES | Resurface Mainline in Okeechobee & Indian River Counties from MP 178.2 to MP 185.0 | Construction - Extinguish the Torch Summary Report | Milling Depth | Roadway | The Contract Plans included 30 different typical sections for milling depths and cross slope correction. Time consuming and confusing for the Contractor to cross reference multiple sheets to determine the appropriate construction sequence. | The EOR should prepare a single page summary exhibit displaying the proposed milling depth and cross slope correction throughout the entire project limits. Do not rely soley on shading to differentiate and identify different pavement depths or ranges.
2019 | E8Q41 | 435165-1, 435165-3, 435167-1, 435167-3 | Christopher NeSmith | Steve Soldati | CES | Resurface Mainline in Okeechobee & Indian River Counties from MP 178.2 to MP 185.0 | Construction - Extinguish the Torch Summary Report | Bridge Joints | Structures | To place the polymer nosing for bridge joints, the asphalt had to be removed all the way to the bridge deck because the polymer nosing will not adhere to asphalt. The thickness of polymer nosing in the Contract Plans was calculated using the 2.25” mill depth rather than using the full depth of the asphalt on the bridge deck. Since the asphalt was much thicker than 2.25” mill depth, the quantity for the polymer nosing had to be significantly overrun. | The EOR should review asphalt pavement condition reports to determine the existing thickness over the bridge decks and the polymer nosing depth for bridge joints should be established based on existing asphalt thickness.
2019 | E8Q77 | 439051-1 | Christopher NeSmith | Steve Soldati | Vibe | ITS Electrical Improvements from MP 185 to MP 235 | Construction - Extinguish the Torch Summary Report | Existing Electrical Service Components | ITS | The Contract Plans did not include the replacement of existing electrical service disconnect boxes and conduit at those boxes at any ITS pole locations. After construction started, it was determined that the existing disconnect boxes were in poor condition and the disconnect boxes and the conduit did not meet current code. | The EOR should conduct a thorough on-site review of existing features to assess their condition and determine the benefit of replacing with new features.
2019 | E8Q77 | 439051-1 | Christopher NeSmith | Steve Soldati | Vibe | ITS Electrical Improvements from MP 185 to MP 235 | Construction - Extinguish the Torch Summary Report | Existing Drainage Structures | Drainage | The Contract Plans indicated open trenching of conduit that conflicted with existing storm drains and drainage features. | The EOR should conduct a thorough review and inspection of existing features, which includes review of existing plans in addition to a field review of the corridor.
2019 | E8N19 | 429350-1 | Tracie Rose | Tom Neyer | TY Lin | Widen Veterans Expy. from Gunn Hwy. to Sugarwood ML Plaza (MP 9.0 to MP 10.727) | Construction - Extinguish the Torch Summary Report | Project Limits | Project Manager | The end of an adjacent project and beginning of this project was located near a bridge structure, which was difficult to coordinate construction phases and transition of traffic approaching and over the bridge. | When possible, locate the point of interface between two adjacent projects away from bridge structures.
2019 | E8N19 | 429350-1 | Tracie Rose | Tom Neyer | TY Lin | Widen Veterans Expy. from Gunn Hwy. to Sugarwood ML Plaza (MP 9.0 to MP 10.727) | Construction - Extinguish the Torch Summary Report | Concrete Surface Finishes | Structures Maintenance | The Contract Plans included an overhead sign structure with concrete columns that extended to the top of an adjacent MSE wall. The MSE wall required a Class V finish but the concrete column did not require any Class V finish, creating an aesthetic issue. | The EOR should identify adjacent concrete structures and determine if the application of consistent surface finish treatments is appropriate.
2019 | E8N52 | 429350-4 | Tracie Rose | Tom Neyer | GAI | Widen Veterans Expy. from Sugarwood ML Plaza to Van Dyke Rd. (MP 10.823 to MP 14.204) | Construction - Extinguish the Torch Summary Report | Project Limits | Project Manager | The Design-Build RFP required the D-B Team to implement Express Lanes outside of the limits of widening and what was designated as the construction limits. | D-B RFP language should ensure that any work required is within the specified construction limits.
2019 | E8N52 | 429350-4 | Tracie Rose | Tom Neyer | GAI | Widen Veterans Expy. from Sugarwood ML Plaza to Van Dyke Rd. (MP 10.823 to MP 14.204) | Construction - Extinguish the Torch Summary Report | Power Service | Electrical | The Contract Plans indicated that the conductors from the utility transformer to the meter at the load center would be installed by the utility provider. During inspection and activation of the power service, the utility provider indicated this was not their responsibility. | The EOR should ensure that the installation of conductors for electrical service from the utility service transformer to the meter/load center are shown to be installed by the contractor, per Turnpike Lighting & Electrical Guide Drawings and FDOT Specifications.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | ITS Conduit | ITS | The Contractor encountered multiple issues during the installation of the larger size wiring needed for the ITS devices on the project due to the size and condition of existing conduit. | The EOR should review typical conduit sizes for locations where wire size has increased and determine if conduit may need to be larger. The EOR should verify the condition of existing conduit and verify if spare conduit is still available prior to identifying its use for future projects.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | ITS Cabinet | ITS | The Contract Plans added a DMS to a site with an existing DMS and proposed using the existing cabinet and existing pull box. The equipment and wiring for the new DMS would not fit in the existing cabinet or be accommodated in the existing pull box. | The EOR should verify the equipment already in an existing cabinet and pull box and determine if they can accommodate required additional equipment and wiring.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | Power Service | Electrical | The existing lighting load centers did not have disconnect switches at the power meters adjacent to the utility provider power poles. Power was turned off to replace the existing load center cabinets with new cabinets, but the utility provider would not turn back on the power until new disconnect switches were provided that met current standards. The Contract Plans: did not include disconnect switches; show existing disconnects to remain; and include an inconsistency between the riser diagram and the wiring schematic detail (which shows two disconnects existing to remain). | The EOR should assess existing load centers to see if they have disconnect switches between the meter and the load center panel and if so determine if the load centers meet current standards. Turnpike Lighting & Electrical Guide Drawings show a service disconnect on the load side of the meter.
2019 | E8P07 | 4356090-1 | Tracie Rose | Tom Neyer | AECOM | Express Lanes Implementation on Veterans Expressway MP 2.911 to MP 10.358 | Construction - Extinguish the Torch Summary Report | Express Lanes | Roadway | The Contract Plans included an entrance point and an exit point of an express lanes in a curve. | The EOR should evaluate the location of the entrance and exit points of express lanes and where possible, they should be located in tangent sections.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Approach Slab | Structures | The Contract Plans called for hydrodemolition of an approach slab due to coring data that seemed to indicate shallow rebar depth. During construction the rebar depth was found to be greater than anticipated resulting in a significantly longer hydrodemolition duration and the determination that full slab replacement would have been more efficient. | In situations where hydrodemolition is being considered the EOR should be sure to have enough data to ensure an accurate gauge of rebar depth over the entire slab.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans called for hydrodemolition of approach slab shoulder and 2 lanes to occur with live traffic directly adjacent to the operation. This posed safety concerns of projectiles hitting vehicles and safety of workers given a lack of buffer area. The work area was decreased in width to provide space for a protection shield and safety of the workers replacing the slab during pouring of concrete. Also, approval was given during construction to close a third lane in order to pour back concrete. | The EOR should prepare MOT plans which take into account the necessary buffer space (recommend min. 5’) for the hydrodemolition equipment and for screeding and finishing the concrete.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Concrete Grooving | Structures | The Contract Plans called for hydrodemolition and concrete replacement in all lanes of an approach slab to occur over a single weekend. In addition, the Plans called for a Class 4 finish and grooving of the approach slab concrete. Due to constraints of lane closure restrictions, mechanical grooving could not be performed prior to opening the travel lanes. requiring manual tining to be performed. | In establishing lane closures, the EOR should ensure that there is enough time for placing and curing of concrete to allow for mechanical grooving per specifications.
2019 | E8R64 | 442631-1 | Tracie Rose | Jason Christopher | AECOM | Veterans Expressway Improvements for Bridge Approaches | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans traffic control required two lanes to be open at all times during construction operations. The project corridor includes 3 general toll lanes and 1 express lane. The express lane ingress was several miles away from the work zone, thus when closures were necessary for the outside lanes the traveling public experienced delays due to the inability to access the express lane and functionally only one lane open to traffic. | The EOR needs to account for the unique operational and access characteristics of express lanes in developing traffic control plans within active express lane corridors.
2019 | E8R57 | 442901-7 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 140 to MP 210 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The Contract Plans included control points that placed the edge of the widening in the center of existing rumble strips. This would have left a portion of the existing rumble strips in place. | The EOR should not rely on as-built information for the development of the Contract Plans. Survey should be performed to locate the existing rumble strips.
2019 | E8R57 | 442901-7 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 140 to MP 210 | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The Contract Plans included the installation of a temporary crash cushion on a bridge. Because the crash cushion requires bolts/anchors to be installed there is the potential to impact the bridge. | The EOR should not propose crash cushions to be installed on bridges unless it is unavoidable.
2019 | E8R57 | 442901-7 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 140 to MP 210 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The EOR assumed the edge of the existing friction course was at the edge of the lane; however, the friction course was offset from the lane similar to an 8” overlap. Also, the inside yellow lane line was designed to transition to the left over 200 to 300 feet; however, the friction course did not include the 200 to 300 foot transition. Per the Contract Plans, either the rumble strips would have been too far from the lane line in the transitions or the rumble strips would have had to transition through the friction course. | The EOR should consider the placement of friction course and rumble strips in transition areas and ensure that rumble strips can be installed according to Standard Plans without cutting through the friction course. Details should be provided for this condition.
2019 | E8R59 | 442901-8 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 210 to MP 249 | Construction - Extinguish the Torch Summary Report | Pavement Design | Roadway | The Contract Plans typical section indicates different optional bases and structural course for the widening of the travel lane versus a new 4' inside shoulder. There are constructability issues associated with the narrow strip of construction needed for the differential design of the travel lane widening. | The EOR should consider the same typical section for travel lane widening and shoulder work when the total width of construction is less than 8’. For ease of construction and simplified paving operations, factor paving efficiency over standard shoulder design criteria in such narrow width pavement areas. This applies to narrow width shoulders, 4' or less, paved with the adjacent travel lane, and other narrow geometry correction locations at transitions, ramps, or gores. Paving efficiency and simplified paving operations also relate to TTCP plan decisions regarding work zones with overnight lane closures, compared to work zones behind temporary barrier wall.
2019 | E8R59 | 442901-8 | Christopher NeSmith | Anil Sharma | Protean | Emergency Shoulder Use Mainline NB MP 210 to MP 249 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The Contract Plans indicate the cross-slope break between the original travel lane and original outside shoulder (2% to 6%) was to remain at the original location with permanent traffic shifted to the left, away from the break. This required the rumble strips to cross the shoulder break, which doesn't meet design criteria. | In this situation the EOR should relocate the shoulder break in relation to the new edge of the outside travel lane to avoid rumble strips crossing into the shoulder break.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Utility Adjustments | Utilities | The Contract Plans included the adjustment of AT&T manholes to be performed by the Contractor. AT&T agreed to perform any adjustments needed. | For impacts to AT&T utilities, the EOR should coordinate with AT&T concerning who will perform the work and obtain a utility work schedule if needed.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Construction Access | Roadway | The Contract Plans included repairs to box culverts where existing dense vegetation and steep slopes were not considered relative to the ability of trucks to access the culverts. Due to steep slopes at some locations, the gunite trucks would have to be located on the edge of the roadway to be able to pump into the box culverts, requiring barrier wall and traffic shifts. | The EOR should evaluate box culvert repair sites for truck access. If necessary, establish Selective Clearing and Grubbing limits and restoration to assure access is possible or include guardrail removal/replacement and placing barrier wall, which would include a lane shift, for culverts which are inaccessible from below.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Rumble Strips | Roadway | The Contractor submitted an RFI for what satisfies the requirement for covering of rumble strips and how it would be paid. | The EOR should specify the cost of filling in rumble strips under 102-2 Special Detour (Lump Sum). The Contract Plans should not quantify temporary asphalt tonnage; however, the Plans should provide width, length, and thickness information so that the Contractor knows the work required by this Special Detour.
2020 | E8Q92 | 437988-1, 437988-3 | Christopher NeSmith | Jason Christopher | Connelly & Wicker | Resurface Mainline in Lake County from MP 287.8 to MP 297.9 | Construction - Extinguish the Torch Summary Report | Embankment | Roadway | The Contract Plans called for inside shoulder treatment per Standard Index 105, Type I. In much of this the non-paved shoulder was being adjusted and required additional fill. This additional fill would not be part of a Type I treatment and was not quantified in the Plans. | When there is embankment shown for shoulder work, the EOR needs to quantify an amount and list it as embankment. The EOR needs to specify Type II Treatment when the area requires fill.
2020 | E8R76 | 439457-1 | Christopher NeSmith | Brandon Bobo | Cumby & Fair | Reconstruct Mainline in Orange County from MP 269.4 to MP 273.3 | Construction - Extinguish the Torch Summary Report | Traffic Control Plans | Roadway | The project section consisted of four lanes in each direction. Without shifting traffic, resurfacing the 2nd lane would have placed workers directly next to the third lane, requiring three lanes to be closed. Due to heavy traffic, a triple-lane closure would have significantly shortened available work time. At certain points in the project, the Contract Plans Traffic Control Plan required the lanes to be shifted onto the shoulder to resurface the 2nd lane, maintain two open lanes, and provide workers with a safe buffer from the open traffic lanes. The resurfacing required a drop-off between resurfaced lanes and the lanes that had not yet been resurfaced. Prior to shifting traffic, the drop-off was at the lane line; however, once the traffic shift was installed, the drop-off was between the vehicles tires. Complaints came in from various travelers on the roadway that the ride was uncomfortable and the condition was perceived to be unsafe. | For projects with deep milling on sections of four or more lanes, the EOR should prepare a Traffic Control Plan that provides traffic shifts, including the use of buffer zones if needed, to assure the drop-offs are contained at the lane lines and that provide for smooth transitions when having to travel across the areas with the drop-offs to the next area where work has not been performed.
2020 | E8R76 | 439457-1 | Christopher NeSmith | Brandon Bobo | Cumby & Fair | Reconstruct Mainline in Orange County from MP 269.4 to MP 273.3 | Construction - Extinguish the Torch Summary Report | Shoulder Cross Slope | Roadway | After resurfacing of the shoulder, water was being retained within the shoulder area, which had not been an existing issue at this location. When the contractor placed temporary pavement to shift traffic onto the shoulder, the existing shoulder slope which included a break, was lost. The contractor continued paving through this section at the same slope as the shoulder coming into where the existing break needed to occur. | The EOR should provide enough detail such that the existing shoulder break condition is clearly depicted or stated in the Contract Plans. The use of "match existing" call-outs do not suffice to provide the necessary information for the contractor to match the existing shoulder conditions.
2021 | E8Q12 | 411406-1, 411406-4 | Fernando Gomez | Snehal Ambare | WGI | Turnpike Widening from Osceola Pkwy to Beachline Expy | Construction - Extinguish the Torch Summary Report | Lane Closures | Traffic Operations | During construction it was anticipated that the plan-specified lane closure hours would be utilized for the necessary detours. This assumption was incorrect and more restrictive detour hours were implemented. | When detours are necessary on a project, ensure the allowable detour hours are specified in the bid documents for road and ramp closures.
2021 | E8Q12 | 411406-1, 411406-4 | Fernando Gomez | Snehal Ambare | WGI | Turnpike Widening from Osceola Pkwy to Beachline Expy | Construction - Extinguish the Torch Summary Report | Lighting Design | Lighting | A specific plan detail was missing on how the internal girder lighting conduits should be routed to the external power source. Reference RFI 513 & 513A. | Design EOR to provide supplemental design details in the plans showing locations and details of conduit runs, power sources, electrical components, and any incidental items needed for completion of box girder lighting systems, in accordance with Department requirements. Coordination between Lighting/Electrical and Structures disciplines required. See FDOT Standard Plan 715-240 and SPI 715-240 (Standard Plan Instructions) for additional information.
2021 | E8Q12 | 411406-1, 411406-4 | Fernando Gomez | Snehal Ambare | WGI | Turnpike Widening from Osceola Pkwy to Beachline Expy | Construction - Extinguish the Torch Summary Report | Concrete Pavement | Roadway | The plan typical sections for concrete pavement specify placing an Optional Base Group 1 (Type-B 12.5) under Plain Cement Concrete Pavement (9 ½”). The associated concrete shoulders that are 5’ or wider are constructed with a variable depth concrete pavement from 9 ½” to 6”. The plans did not specify that the added base under the variable depth should be incidental to the base construction and the contractor requested compensation since the item is paid by the square yard and is a plan quantity item. | Future contracts that utilize concrete pavement with tapered shoulders should include a note on the typical sections that states the base wedge is incidental to the base item.
2021 | E8R51 | 441322-1 | Fernando Gomez | Francisco Cardona / Ruby Monsalve | Hardesty & Hanover | AET Northern Coin Conversion | Construction - Extinguish the Torch Summary Report | Barrier Wall | Roadway | The contractor was required to leave approximately 5,000 feet of Type K Barrier Wall in place along both sides of the median for future use. The plans did not address any special requirements for the wall to remain – no condition requirements, no class 5 finish, no requirement that it be new wall, etc. This created much debate from the contractor in the closeout process. | Since this wall is a semi-permanent feature until removed for a future widening, the project would have benefited from having a specific item for this wall to remain so the contractor could have bid the cost of new wall eliminating controversy and providing a better product.
2021 | E8Q95 | 436520-1 | Christopher NeSmith | Jason Christopher | PGA | Ressurface Polk Parkway MP 0 to MP 8 | Construction - Extinguish the Torch Summary Report | Modeling | Roadway | Occasionally during operation, the AMG equipment would suddenly send the miller or paver to an unusual milling depth or asphalt grade. | EOR to ensure all lines/triangles are connected and no gaps or irregularities on the 3D surfaces.
2021 | E8Q95 | 436520-1 | Christopher NeSmith | Jason Christopher | PGA | Ressurface Polk Parkway MP 0 to MP 8 | Construction - Extinguish the Torch Summary Report | Lane Widths | Roadway | When comparing the measured quantities of milling and paving to the SQ sheets we have found substantial differences resulting in significant quantity overruns of approximately $292K combined. All lane widths were measured during each operation by the Contractor QC and the CEI VT. Our The field measured quantities do not match the SQ sheets because the Model and measured lane widths differ. | The lane widths in the model should be set at 12 foot exact, not match existing survey/topo/3D.
2024 | Various | Various | NA | NA | Various | Underdeck Lighting (Spec 715 - Highway Lighting) | Turnpike Structures | Lighting Design | Lighting | The APL options for "LED Luminaire, (Underdeck)" now include wall-mounted fixtures that extend much further (2.5 ft +) than their predecessors. They are being designed (photometrics) and detailed to be mounted to pier caps and/or MSE copings without verification (or documentation) or enough plan dimensions to ensure the proposed fixture meets the clearance requirements (vertical, horizontal, lateral offset) specified by FDM. | The lighting and structural EOR should coordinate on the determination of lighting mounting heights on bridge elements to ensure the proposed fixture meets the clearance requirements (vertical, horizontal, lateral offset) specified by FDM. Please pay special attention to FDM 260.6 and its figures and consider tilt angles and fixture size. Plan details and tables must provide adequate dimensions and information to ensure the Contractor will position the fixture so that it meets both the required clearances and the photometric design assumptions. The lighting design documentation should include calculations, sketches, survey info, etc. to show that the proposed design meets criteria.