## Score Tool
QA Audit Score Tool
Contract / FPID:
Submittal Phase: | Date:
Submitted Document | Discipline | QC document submitted (Y/N) | A. QC Document sheet count. (If QC document is not present, INPUT the submitted document sheet count) | B. Staffing Plan | C. 5-step Review Procedure | D. BIM review procedure | E. Certificate of compliance & CPAM Checklist | Notes: provide comments for the scores given.
BIM Review files (Item D) | [5 empty] | N/A
Certificate of compliance & CPAM Checklist (Item E) | [6 empty] | 1 | CPAM missing
Ex. Document 1 |  | Yes | 50 | 1 | 3 |  |  | Lead Technical Professional (LTP) and QC reviewer doesn’t match the QAQC Staffing Plan
Ex. Document 2 |  | Yes | 100 | 3 | 1 |  |  | Initials missing in the QC stamp, inconsistent colors used
Ex. Document 3 |  | No | 100 | N/A | N/A |  |  | Did not provide QC document
Ex. Document 4 |  | Yes | 100 | 3 | 3 |  |  | Meet all the guideline criteria
Calculation |  | 75% | 71.43% | 2.6 | 2.2
Recommended Score |  |  | 2 | 2.5 | 2 | N/A | 1 | Insert these scores in the QA Audit form

## Dropdown lists
Yes | Drainage | N/A | 1
No | Estimates | 1 | 2
| Geotech | 2 | 3
| ITS | 3
Landscape
Lighting
Roadway
S&P Marking
Signalization
Structures
Toll Facilities
TTC